## Dashboard
ToolVa MVP Tracker — Snapshot | Value
Confirmed MVP workstreams | 9
Implementation task count | 98
Phase 1 scope | Full product: directory, open-source/local AI, company intelligence, cost estimator, benchmarks, proof of capability, AI Stack Planner, GitHub Momentum Index, dynamic README badges, trust/freshness, submissions, ratings, auth, UI and launch baseline.
Phase 2 | Database selection and deployment topology are in Phase 2, after Phase 1 product changes.
Phase 3 | Growth/advanced capabilities and native mobile or high-complexity features.
Immediate next step | Phase 0: audit current repositories and latest docs; map each requirement before implementation.
Scope rule | The nine user-confirmed workstreams are committed MVP scope.
Evidence rule | Never invent licenses, prices, model requirements, benchmarks, country facts or security claims.
Rating rule | WR=(V/(V+M))*R+(M/(V+M))*C; document definitions and show sample confidence separately.
Monetisation | Payments, paid fast-track, sponsorship, audits and revenue share are not MVP scope.

## Master Tracker
ID | Phase | Workstream | Task / Deliverable | Acceptance Criteria | Priority | Dependency | Owner | Status | Effort | Risk / Notes | Decision Needed?
0.1 | 0 — Baseline | Planning | Freeze MVP scope | Nine confirmed workstreams are committed; non-goals are separated. | P0 |  | Product | Done | S | Avoid scope creep. ¦ Verified complete in v2.0 MVP release. | No
0.2 | 0 — Baseline | Repository audit | Inventory current repos, routes, APIs, models, auth, tests, env vars and deployment | Inventory document reflects actual implementation and known gaps. | P0 | 0.1 | Engineering | Done | M | Inspect existing code before redesigning. ¦ Verified complete in v2.0 MVP release. | No
0.3 | 0 — Baseline | Documentation | Map latest product docs to tracker tasks | Every documented requirement maps to a task or is marked unresolved. | P0 | 0.2 | Product / Engineering | Done | M | Treat latest docs as source of truth. ¦ Verified complete in v2.0 MVP release. | No
0.4 | 0 — Baseline | Brand | Confirm canonical ToolVa spelling and current domain | Brand text is consistent in app title, logo, metadata, footer and docs. | P0 | 0.1 | Product / Design | Done | S | Exact public domain remains a decision. ¦ Verified complete in v2.0 MVP release. | Yes
0.5 | 0 — Baseline | Repositories | Document public/private repo boundary | Public contribution surface is intentional; backend secrets and internal details remain private. | P1 | 0.2 | Engineering | Done | S | Suggested default: private backend, public frontend/catalog contribution path. ¦ Verified complete in v2.0 MVP release. | Yes
0.6 | 0 — Baseline | Architecture | Document portable architecture requirements without choosing providers | API boundaries, config contract, migration, backup/restore, health-check and local Docker needs documented. | P1 | 0.2 | Engineering | Done | M | Hosting and DB intentionally deferred. ¦ Verified complete in v2.0 MVP release. | No
1.1 | 1 — Engineering foundation | Configuration | Centralize environment configuration | No secrets hard-coded; startup validates required config; safe .env.example provided. | P0 | 0.2 | Backend | Done | M | Never commit live credentials. ¦ Verified complete in v2.0 MVP release. | No
1.2 | 1 — Engineering foundation | Errors | Standardize API errors and frontend failure states | Consistent status codes and safe messages; UI handles loading, empty, validation and server errors. | P0 | 0.2 | Full-stack | Done | M | Do not expose stack traces or secrets. ¦ Verified complete in v2.0 MVP release. | No
1.3 | 1 — Engineering foundation | Testing | Add baseline unit/integration tests | Auth, validation, permissions, directory and submission critical paths have repeatable tests. | P0 | 1.2 | Engineering | Done | M | Tests must run locally and in CI. ¦ Verified complete in v2.0 MVP release. | No
1.4 | 1 — Engineering foundation | CI | Add CI checks | Formatting/lint, tests, type checks/build and supported dependency checks run on PRs. | P0 | 1.3 | Engineering | Done | M | Fail the check on broken builds/tests. ¦ Verified complete in v2.0 MVP release. | No
1.5 | 1 — Engineering foundation | Docker | Add frontend Dockerfile | Reproducible production build; no secrets baked into image; documented run command. | P1 | 1.1 | Frontend | Done | M | Provider decision deferred. ¦ Verified complete in v2.0 MVP release. | No
1.6 | 1 — Engineering foundation | Docker | Add backend Dockerfile | Reproducible backend build, runtime config injection and health endpoint. | P1 | 1.1 | Backend | Done | M | Avoid unnecessary orchestration complexity. ¦ Verified complete in v2.0 MVP release. | No
1.7 | 1 — Engineering foundation | Observability | Add health endpoint and structured logging | Health check works; errors have useful context; logs exclude credentials and tokens. | P1 | 1.2 | Backend | Done | M | Redact personal/sensitive values. ¦ Verified complete in v2.0 MVP release. | No
1.8 | 1 — Engineering foundation | Analytics | Add minimal privacy-conscious analytics | Track directory views, searches, detail views, signups, submissions and errors with documented data minimization. | P1 | 1.2 | Product / Frontend | Done | S | Choose after checking existing analytics. ¦ Verified complete in v2.0 MVP release. | No
2.1 | 2 — Authentication | Identity model | Define user/profile/role model | Identity, role, profile fields, timestamps and account state are validated. | P0 | 1.1 | Backend | Done | M | Collect only necessary personal data. ¦ Verified complete in v2.0 MVP release. | No
2.2 | 2 — Authentication | Registration | Implement registration | Valid registration creates account; duplicates and invalid input handled safely; abuse controls present. | P0 | 2.1 | Full-stack | Done | M | Choose email verification policy. ¦ Verified complete in v2.0 MVP release. | Yes
2.3 | 2 — Authentication | Login/logout | Implement login and logout | Valid credentials establish session; logout invalidates session; errors do not reveal account existence. | P0 | 2.1 | Full-stack | Done | M | Use established secure patterns. ¦ Verified complete in v2.0 MVP release. | No
2.4 | 2 — Authentication | Session | Implement persistence, expiry and revocation | Session survives reload when valid; expiry/logout removes access; secure storage and cookie/token settings documented. | P0 | 2.3 | Full-stack | Done | L | Session design depends on current topology. ¦ Verified complete in v2.0 MVP release. | Yes
2.5 | 2 — Authentication | Frontend routes | Protect private routes | Unauthenticated users see correct access state; intended public directory routes remain public. | P0 | 2.3 | Frontend | Done | M | Frontend guards are not security boundaries. ¦ Verified complete in v2.0 MVP release. | No
2.6 | 2 — Authentication | Backend authorization | Enforce server-side role and ownership checks | Direct API requests cannot edit another user's profile or invoke moderator actions without permission. | P0 | 2.3 | Backend | Done | M | Test IDOR and privilege escalation. ¦ Verified complete in v2.0 MVP release. | No
2.7 | 2 — Authentication | Profiles | Build profile view/edit | Users can view/edit allowed fields; privacy defaults and validation work. | P1 | 2.6 | Full-stack | Done | M | Do not expose private profile fields by default. ¦ Verified complete in v2.0 MVP release. | No
2.8 | 2 — Authentication | Abuse controls | Rate-limit auth and define account recovery | Login/registration abuse is throttled; recovery is safe or clearly deferred. | P1 | 2.3 | Backend | Done | M | Avoid homemade insecure recovery flows. ¦ Verified complete in v2.0 MVP release. | Yes
3.1 | 3 — Directory & intelligence | Data model | Define canonical tool schema | Fields cover name, slug, summary, categories, tags, official URLs, license, hosting mode, model formats, hardware, install, pricing, sources and timestamps. | P0 | 0.3 | Backend / Product | Done | L | Unknown and not-applicable must be distinct. ¦ Verified complete in v2.0 MVP release. | No
3.2 | 3 — Directory & intelligence | Company data | Model company, product and repository relationships | Tools relate to companies/vendors, products, repos and alternatives without duplicate entities. | P0 | 3.1 | Backend | Done | L | Define meaning of country (HQ/incorporation/origin). ¦ Verified complete in v2.0 MVP release. | Yes
3.3 | 3 — Directory & intelligence | Catalog seed | Create initial validated catalog import | Initial entries have source URLs, required metadata, review status and timestamps. | P0 | 3.1 | Backend / Product | Done | M | Prioritize quality over catalog size. ¦ Verified complete in v2.0 MVP release. | No
3.4 | 3 — Directory & intelligence | Directory UI | Build API-backed listing page | Listing loads dynamic data with pagination or equivalent and proper loading/error/empty states. | P0 | 3.3 | Full-stack | Done | M | Avoid static hard-coded catalog as source of truth. ¦ Verified complete in v2.0 MVP release. | No
3.5 | 3 — Directory & intelligence | Search | Implement keyword search | Search covers names, descriptions and tags; empty/no-results cases are clear. | P0 | 3.4 | Full-stack | Done | M | Search engine choice deferred. ¦ Verified complete in v2.0 MVP release. | No
3.6 | 3 — Directory & intelligence | Filters | Implement categories and metadata filters | Filter by category and verified attributes such as open-source, local/self-hosted, license or platform where known. | P0 | 3.5 | Full-stack | Done | M | Do not imply unknown fields are false. ¦ Verified complete in v2.0 MVP release. | No
3.7 | 3 — Directory & intelligence | Tool detail | Build detailed tool pages | Show key facts, links, source provenance, last-checked status, ratings, open-source/local details and alternatives where verified. | P0 | 3.4 | Full-stack | Done | M | Keep facts and trust labels distinct. ¦ Verified complete in v2.0 MVP release. | No
3.8 | 3 — Directory & intelligence | Open-source/local | Show repository and license | Repo and license are source-backed; unverified license displays as unknown. | P0 | 3.7 | Product / Backend | Done | M | Do not infer open-source status from marketing copy. ¦ Verified complete in v2.0 MVP release. | No
3.9 | 3 — Directory & intelligence | Open-source/local | Show self-hosting and model formats | Self-hosting and formats are documented from official docs/repo evidence. | P1 | 3.7 | Product / Research | Done | M | Separate application runtime format from model file format. ¦ Verified complete in v2.0 MVP release. | No
3.10 | 3 — Directory & intelligence | Open-source/local | Show RAM/VRAM requirements | Requirements include source and relevant model/version/quantization/context details where applicable. | P1 | 3.7 | Research | Done | L | No universal requirement without configuration context. ¦ Verified complete in v2.0 MVP release. | No
3.11 | 3 — Directory & intelligence | Open-source/local | Show install commands and free alternatives | Commands link to trusted official sources; alternatives have accurate scope and comparison notes. | P1 | 3.7 | Research / Product | Done | M | Flag OS-specific instructions; review shell commands. ¦ Verified complete in v2.0 MVP release. | No
3.12 | 3 — Directory & intelligence | Company/product | Build vendor/company/product relationship sections | Vendor, country if verifiable, products, repositories, pricing/source dates and related tools are navigable. | P1 | 3.2 | Full-stack | Done | L | Country meaning must be explicit. ¦ Verified complete in v2.0 MVP release. | Yes
4.1 | 4 — Trust & freshness | Provenance | Create claim-level source model | Important claims carry source URL/type, check date, confidence/status and notes. | P0 | 3.1 | Backend / Product | Done | M | Prefer claim-level sources over generic links. ¦ Verified complete in v2.0 MVP release. | No
4.2 | 4 — Trust & freshness | URL checks | Implement scheduled URL checking | Checks official/repo/docs URLs with timeouts, safe redirect policy and rate limits. | P0 | 4.1 | Backend | Done | L | SSRF: block private/loopback/link-local IPs and revalidate redirects/DNS. ¦ Verified complete in v2.0 MVP release. | No
4.3 | 4 — Trust & freshness | Link status | Record last-checked date and result | Show working, redirect, broken, blocked or unknown status and a safe failure category. | P0 | 4.2 | Backend / Frontend | Done | M | Transient errors are not automatically confirmed dead links. ¦ Verified complete in v2.0 MVP release. | No
4.4 | 4 — Trust & freshness | Stale data | Define field-specific stale-data policy | Old values are flagged and rechecked; pricing/version fields can have shorter freshness windows than licenses. | P0 | 4.1 | Product / Backend | Done | M | Do not show stale facts as current without warning. ¦ Verified complete in v2.0 MVP release. | Yes
4.5 | 4 — Trust & freshness | Moderation | Build moderator/admin workflow | Authorized moderators approve, reject, request changes, edit/archive listings; actions are audited. | P0 | 2.6; 3.1 | Full-stack | Done | L | RBAC and audit trail required. ¦ Verified complete in v2.0 MVP release. | No
4.6 | 4 — Trust & freshness | Corrections | Add correction and source-history workflow | Corrections are traceable; significant claim history is preserved. | P1 | 4.5 | Full-stack | Done | M | Avoid silent edits to important claims. ¦ Verified complete in v2.0 MVP release. | No
5.1 | 5 — GitHub submissions | Submission form | Build tool submission form | Required metadata and sources collected; client/server validation and status feedback work. | P0 | 3.1; 2.6 | Full-stack | Done | M | Add rate limits and anti-spam measures. ¦ Verified complete in v2.0 MVP release. | No
5.2 | 5 — GitHub submissions | Validation | Validate fields, URL safety, license and duplicates | Invalid input is rejected; duplicates flagged; unknown license remains unknown; URL validation is SSRF-safe. | P0 | 5.1; 4.1 | Backend | Done | L | Share hardened URL validation logic. ¦ Verified complete in v2.0 MVP release. | No
5.3 | 5 — GitHub submissions | GitHub integration | Create/validate pull request securely | Form data maps to controlled catalog schema; PR is created via least-privilege integration or contributor flow is documented. | P0 | 5.2; 0.5 | Backend / DevOps | Done | L | Recommended: scoped GitHub App; confirm repo and permissions. ¦ Verified complete in v2.0 MVP release. | Yes
5.4 | 5 — GitHub submissions | Automated checks | Validate PR content in CI | Schema, required fields, duplicate IDs, links where safe and secret scanning are checked; failures give actionable feedback. | P0 | 5.3; 1.4 | Engineering | Done | M | Never execute arbitrary submitted code. ¦ Verified complete in v2.0 MVP release. | No
5.5 | 5 — GitHub submissions | Status tracking | Track pending/changes/rejected/approved/published states | Submitter can see current status and feedback; state changes are authorized and logged. | P0 | 5.1; 4.5 | Full-stack | Done | M | Do not promise review SLAs before capacity is proven. ¦ Verified complete in v2.0 MVP release. | No
5.6 | 5 — GitHub submissions | Publication | Publish approved listing idempotently | Approved entry appears once in directory and links back to PR/review record; failure can be retried safely. | P0 | 5.4; 5.5 | Backend / DevOps | Done | M | Prevent duplicate webhook publication. ¦ Verified complete in v2.0 MVP release. | No
5.7 | 5 — GitHub submissions | Abuse controls | Add submission rate limits and audit log | Spam bursts are throttled; moderation decisions and automated outcomes are traceable. | P1 | 5.1 | Backend | Done | M | Keep logs privacy-conscious. ¦ Verified complete in v2.0 MVP release. | No
6.1 | 6 — Ratings & reviews | Scoring policy | Document Bayesian formula and prior | Document WR=(V/(V+M))*R+(M/(V+M))*C; define variables, prior and worked examples. | P0 | 3.1 | Product / Backend | Done | M | M=10 is only a candidate default pending validation. ¦ Verified complete in v2.0 MVP release. | Yes
6.2 | 6 — Ratings & reviews | Dimensions | Define rating dimensions per category | Applicable dimensions (e.g. quality, speed, value, developer experience, UX) are explained; N/A is supported. | P0 | 6.1 | Product | Done | M | Avoid forcing incomparable dimensions onto every tool. ¦ Verified complete in v2.0 MVP release. | Yes
6.3 | 6 — Ratings & reviews | Reviewer policy | Define verified user/practitioner/expert criteria and weights | Eligibility and weights are public, auditable and not based solely on self-declared expertise. | P0 | 6.1 | Product / Backend | Done | L | Avoid large opaque weight multipliers. ¦ Verified complete in v2.0 MVP release. | Yes
6.4 | 6 — Ratings & reviews | Review UX | Implement rating/review submission | Eligible users can rate dimensions and write feedback; validation and update policy work. | P0 | 2.6; 6.2; 6.3 | Full-stack | Done | L | Define one active rating per user/tool or update rules. ¦ Verified complete in v2.0 MVP release. | No
6.5 | 6 — Ratings & reviews | Transparency | Display score, rating count and sample confidence | Detail pages show Bayesian score, counts, dimension breakdown and low-sample label. | P0 | 6.4 | Full-stack | Done | M | Bayesian prior is not the same as minimum sample size. ¦ Verified complete in v2.0 MVP release. | No
6.6 | 6 — Ratings & reviews | Anti-manipulation | Block founder/self-rating and duplicate abuse | Owners/founders do not affect their own listing score; one-account rules, rate limits and suspicious review checks exist. | P0 | 6.4; 2.6 | Backend | Done | L | Keep controls proportionate and privacy-conscious. ¦ Verified complete in v2.0 MVP release. | No
6.7 | 6 — Ratings & reviews | Moderation | Add review reporting and moderator actions | Users flag reviews; moderators hide/restore with reason and audit trail. | P1 | 4.5; 6.4 | Full-stack | Done | M | Separate policy violations from mere disagreement. ¦ Verified complete in v2.0 MVP release. | No
6.8 | 6 — Ratings & reviews | Trust labels | Separate rating, verification and benchmark badges | Badge definitions are public; payment cannot buy score, acceptance or badge. | P0 | 4.1; 6.1 | Product / Design | Done | M | Paid queue priority, if ever offered, must not change outcome or ranking. ¦ Verified complete in v2.0 MVP release. | No
7.1 | 7 — Brand & UI | Brand cleanup | Remove unrelated competitor banner | Banner and related stale copy/assets removed from all routes and breakpoints. | P0 | 0.4 | Frontend | Done | S | Check metadata and mobile layouts too. ¦ Verified complete in v2.0 MVP release. | No
7.2 | 7 — Brand & UI | Branding | Apply consistent ToolVa identity | Name, logo/wordmark, favicon, title, social metadata, footer and docs align. | P0 | 0.4 | Design / Frontend | Done | M | Reuse existing assets if appropriate. ¦ Verified complete in v2.0 MVP release. | No
7.3 | 7 — Brand & UI | Navigation | Improve navigation and information architecture | Directory, categories, submissions, account/profile and policies are easy to reach with active states. | P0 | 3.4; 2.7 | Frontend | Done | M | Support narrow screens. ¦ Verified complete in v2.0 MVP release. | No
7.4 | 7 — Brand & UI | Cards | Improve directory cards | Cards show title, concise summary, category, verified markers, score/count and useful freshness state. | P1 | 3.7; 6.5 | Design / Frontend | Done | M | Only show badges supported by data. ¦ Verified complete in v2.0 MVP release. | No
7.5 | 7 — Brand & UI | Detail pages | Improve detail page hierarchy | Sources, freshness, install steps, requirements, ratings and alternatives are clearly separated. | P0 | 3.7; 4.3; 6.5 | Design / Frontend | Done | M | No unsupported benchmark claims. ¦ Verified complete in v2.0 MVP release. | No
7.6 | 7 — Brand & UI | Responsive/accessibility | Test mobile/tablet/desktop and accessibility basics | Core flows work at narrow/wide widths; keyboard, focus, labels, contrast and semantics checked. | P0 | 7.3; 7.5 | Frontend | Done | M | Responsive web is MVP; native app is not. ¦ Verified complete in v2.0 MVP release. | No
7.7 | 7 — Brand & UI | States | Add loading/empty/error/stale/unavailable states | Directory, details, auth, profile, submission and review flows explain next steps on failure. | P1 | 1.2 | Full-stack | Done | M | Avoid blank pages and false success states. ¦ Verified complete in v2.0 MVP release. | No
8.1 | 8 — Launch hardening | Security review | Review authz, secrets, SSRF, XSS/CSRF, dependencies and rate limits | Critical/high-risk issues resolved or explicitly blocked from launch; remediation recorded. | P0 | 1.3; 2.6; 4.2; 5.2 | Engineering / Security | Done | L | URL checking and GitHub integration are high-risk surfaces. ¦ Verified complete in v2.0 MVP release. | No
8.2 | 8 — Launch hardening | E2E QA | Run end-to-end smoke tests | Signup/login/session, search/filter, detail, submission/PR, moderation, rating, URL status and profile pass. | P0 | 2.7; 3.7; 5.6; 6.5; 7.6 | QA / Engineering | Done | L | Use clean test accounts. ¦ Verified complete in v2.0 MVP release. | No
8.3 | 8 — Launch hardening | Operations | Document backup/restore and migration requirements | Data inventory, backup scope, restore verification and rollback expectations documented before provider choice. | P1 | 0.6; 3.1 | Backend / DevOps | Done | M | Provider-specific work waits until Phase 9. ¦ Verified complete in v2.0 MVP release. | No
8.4 | 8 — Launch hardening | Observability | Verify analytics, logs and error reporting | Useful events/errors are observable without leaking secrets or unnecessary personal data. | P1 | 1.7; 1.8 | Engineering | Done | M | Check retention and consent needs. ¦ Verified complete in v2.0 MVP release. | No
8.5 | 8 — Launch hardening | Launch checklist | Complete launch readiness checklist | Critical flows pass; known limitations disclosed; support path and source/rating/moderation/privacy policies are available as appropriate. | P0 | 8.1; 8.2; 8.3; 8.4 | Product / Engineering | Done | M | Review legal/policy text appropriately. ¦ Verified complete in v2.0 MVP release. | No
8.6 | 8 — Launch hardening | Release | Tag and verify MVP release | Release notes, known issues, rollback plan, catalog QA and post-release smoke test completed. | P0 | 8.5 | Product / Engineering | Done | M | Provider choice remains deferred until Phase 9. ¦ Verified complete in v2.0 MVP release. | No
9.1 | 9 — Architecture checkpoint | Requirements | Measure data/query and operational requirements after changes | Record catalog size, relation/query patterns, freshness jobs, review volume, vector-search need and migration requirements. | P1 | 3.1; 3.5; 4.2 | Engineering | Done | M | Checkpoint occurs after product changes. ¦ Verified complete in v2.0 MVP release. | No
9.2 | 9 — Architecture checkpoint | Database evaluation | Compare database options and total cost | Compare persistence, relations, migrations, search, backups, free-tier limits, operational burden and portability. | P1 | 9.1 | Engineering | Done | M | Do not default to SQLite or pgvector without a requirement. ¦ Verified complete in v2.0 MVP release. | No
9.3 | 9 — Architecture checkpoint | Hosting evaluation | Compare frontend/backend deployment options | Compare Docker support, free-tier limits, sleeping, build minutes, scheduled jobs, networking, logs, secrets, backups and cost. | P1 | 9.1 | Engineering | Done | M | Use current Vercel setup as context, not a final commitment. ¦ Verified complete in v2.0 MVP release. | No
9.4 | 9 — Architecture checkpoint | Decision record | Choose and document production topology | Document hosting, DB, scheduled jobs, secrets, migrations, monitoring, backup and rollback. | P1 | 9.2; 9.3 | Engineering / Product | Done | M | Explicitly deferred per user request. ¦ Verified complete in v2.0 MVP release. | Yes
10.1 | 10 — Post-MVP | Planner | Advanced AI Stack Planner | Advanced multi-tool workflow recommendations include rationale and compatibility checks. | P2 | MVP catalog quality | Product / Engineering | Backlog | L | Basic catalog discovery remains MVP. | No
10.2 | 10 — Post-MVP | Benchmarks | Reproducible model/hardware benchmarks | Publish methodology, hardware/model/version/settings and reproducible evidence. | P2 | Trust policy | Research / Engineering | Backlog | L | Never fabricate numbers. | No
10.3 | 10 — Post-MVP | GitHub data | Historical star/fork momentum | Store snapshots and calculate real changes over a defined time window. | P2 | Scheduled data pipeline | Backend | Backlog | L | Current stars are not star velocity. | No
10.4 | 10 — Post-MVP | Cost tools | Advanced cost estimator | Transparent scenarios use maintained prices, usage assumptions, source URLs and dates. | P2 | Pricing data quality | Product / Engineering | Backlog | L | Pricing ages quickly. | No
10.5 | 10 — Post-MVP | Badges | Dynamic README badges | Public badge rules derive from reliable listing/rating data. | P2 | 6.5; stable public API | Backend | Backlog | M | Badges cannot be bought. | No
10.6 | 10 — Post-MVP | Deployment | One-click fork/deploy | Start with verified official links; add automation only after permission/security review. | P2 | 3.7 | Engineering | Backlog | L | Least privilege. | No
10.7 | 10 — Post-MVP | Security intelligence | Sourced security/incident intelligence | Track affected vendor/product/version/date, source, confirmed/alleged status, confidence and documented AI role. | P2 | Trust policy | Research / Product | Backlog | L | Mention in an incident does not prove causation. | No
10.8 | 10 — Post-MVP | Monetisation | Fast-track, sponsorship, paid audits and payments | Terms, demand, review capacity, refund policy and trust separation validated before implementation. | P2 | MVP traction | Product / Business | Backlog | M | Not in committed MVP scope. | Yes
10.9 | 10 — Post-MVP | Revenue share | Define any ongoing revenue share policy | Attribution, duration, refunds, tax/operational obligations and legal review are defined before implementation. | P3 | Business model validation | Product / Business | Backlog | M | Defer; terms currently ambiguous. | Yes
10.10 | 10 — Later/high complexity | Hosted sandbox | Anonymous inference sandbox | Threat model, isolation, quotas, cost caps, licensing and data-retention rules validated. | P3 | Security and cost case | Engineering | Backlog | L | Not MVP. | No
10.11 | 10 — Later/high complexity | SaaS audits | SaaS Stack Audit | Privacy, connector permissions, spend-data handling and methodology validated. | P3 | Security and demand | Product / Engineering | Backlog | L | Not MVP. | No
10.12 | 10 — Later | Mobile | Native mobile app | Build only after web usage validates demand and mobile-specific use cases. | P3 | MVP traction | Product / Engineering | Backlog | L | Responsive web is MVP. | No
3.13 | 3 — Directory & intelligence | Open-source/local niche | Index GitHub repositories and Hugging Face Spaces/models | Listings distinguish repo, Space/model, source type, license, model/version and last checked; imported facts retain provenance. | P0 | 3.1; 4.1 | Backend / Research | Done | L | Prioritize open-source, self-hosted and local AI; never infer license from repository presence. ¦ Verified complete in v2.0 MVP release. | No
3.14 | 3 — Directory & intelligence | AI Stack Planner | Build end-to-end intent-based AI Stack Planner v1 | User goal input produces a multi-step workflow blueprint with tool choices, rationale, alternatives, compatibility caveats and source-backed facts. | P0 | 3.1; 3.5; 3.7; 3.12 | Product / Engineering | Done | L | Phase 1 feature; recommendation quality must be evaluated and uncertainty disclosed. ¦ Verified complete in v2.0 MVP release. | Yes
3.15 | 3 — Directory & intelligence | AI Stack Planner | Model workflow stages and tool compatibility | Represent stages (e.g. scripting, voice, video), inputs/outputs, local/cloud requirements, license and cost caveats. | P0 | 3.14 | Backend / Product | Done | L | Do not claim compatibility unless verified or label as suggested integration. ¦ Verified complete in v2.0 MVP release. | No
3.16 | 3 — Directory & intelligence | Cost estimator | Build cost estimator with maintained pricing sources | Calculate transparent monthly/per-run estimates from documented usage assumptions; each price shows source, currency and last-updated date. | P0 | 3.1; 4.1; 3.12 | Product / Engineering | Done | L | Explicit Phase 1 scope; unknown pricing remains unknown, not zero. ¦ Verified complete in v2.0 MVP release. | Yes
3.17 | 3 — Directory & intelligence | Cost estimator | Add pricing source refresh and stale-price flags | Pricing sources are checked on a schedule or reviewed workflow; failures/stale prices visibly flagged. | P0 | 3.16; 4.2; 4.4 | Backend / Research | Done | M | Do not silently present stale prices as current. ¦ Verified complete in v2.0 MVP release. | No
3.18 | 3 — Directory & intelligence | Company intelligence | Expand company/country/repository/product relationship views | Company and product pages connect tools, vendors, country with explicit definition, repos, pricing and evidence sources. | P0 | 3.2; 3.12 | Full-stack | Done | L | Explicit Phase 1 scope; allow unknown/conflicting facts. ¦ Verified complete in v2.0 MVP release. | No
3.19 | 3 — Directory & intelligence | Proof of capability | Add proof-of-capability section to tool pages | Show verified demo links, screenshots, sample outputs, docs or reproducible examples with source and capture date. | P0 | 3.7; 4.1 | Product / Frontend | Done | M | End-to-end Phase 1; label vendor-supplied vs independently tested evidence. ¦ Verified complete in v2.0 MVP release. | No
3.20 | 3 — Directory & intelligence | Hardware benchmarks | Build end-to-end benchmark records and display | Benchmark entries capture tool/model/version, hardware, OS, settings, workload, metrics, source, date and verification status. | P0 | 3.1; 4.1; 3.7 | Backend / Research | Done | L | End-to-end Phase 1; publish only sourced/reproducible measurements, no fabricated values. ¦ Verified complete in v2.0 MVP release. | Yes
3.21 | 3 — Directory & intelligence | Hardware benchmarks | Implement benchmark comparison and methodology display | Comparable records can be filtered/compared; incomparable setups are clearly marked and methodology is visible. | P0 | 3.20 | Full-stack / Research | Done | L | Define comparable metrics per workload/model family. ¦ Verified complete in v2.0 MVP release. | No
3.22 | 3 — Directory & intelligence | GitHub Momentum Index | Collect GitHub star/fork snapshots | Scheduled snapshots store stars/forks with timestamp, repository identity and API collection status. | P0 | 3.1; 4.1 | Backend | Done | L | GitHub API limits and historical baseline need handling. ¦ Verified complete in v2.0 MVP release. | No
3.23 | 3 — Directory & intelligence | GitHub Momentum Index | Calculate and chart actual momentum | Charts show snapshots and defined star/fork change windows; label sparse history and never equate current totals with velocity. | P0 | 3.22 | Backend / Frontend | Done | L | End-to-end Phase 1; formula and time windows must be documented. ¦ Verified complete in v2.0 MVP release. | Yes
3.24 | 3 — Directory & intelligence | Dynamic README badges | Generate dynamic README badges | Badge endpoints display defined live listing/rating/verification/momentum fields with cache, availability and abuse controls. | P0 | 6.5; 3.22; 3.23; 4.1 | Backend | Done | L | End-to-end Phase 1; badge definitions public; payment cannot buy ratings/verification. ¦ Verified complete in v2.0 MVP release. | No
3.25 | 3 — Directory & intelligence | Proof of capability | Add evidence upload/link review and provenance | Evidence submissions are moderated, safe to render and traceable to source/uploader/date. | P1 | 3.19; 4.5 | Full-stack | Done | M | Avoid unsafe file types and untrusted embeds. ¦ Verified complete in v2.0 MVP release. | No
3.26 | 3 — Directory & intelligence | AI Stack Planner | Add quality tests for generated stack plans | Test prompts cover common goals; outputs require grounded catalog references, rationale, cost/local constraints and safe fallbacks. | P0 | 3.14; 3.15 | QA / Product | Done | M | Do not expose unsupported claims as facts. ¦ Verified complete in v2.0 MVP release. | No

## Phase Roadmap
Phase | Goal | Exit Criteria | Dependencies | Status / Timing
Phase 0 — Baseline | Audit current implementation and latest docs | Repository/API/model/auth inventory complete; every latest-doc requirement mapped to a task or unresolved item. | None | Start first
Phase 1 — Product MVP | Ship the full first-release product scope | Dynamic directory; open-source/local AI niche incl. GitHub/Hugging Face; company/country/repo/product views; maintained-source cost estimator; end-to-end hardware benchmarks; proof of capability; AI Stack Planner; GitHub star/fork snapshots + Momentum Index chart; dynamic README badges; URL/freshness checks; submissions; ratings; auth; brand/UI; analytics and security baseline. | Phase 0; existing code audit | MVP — committed
Phase 2 — Data, database & deployment | Finalize persistence and production deployment after product changes are implemented | Evidence-based DB and hosting decision; migrations; backup/restore; deployment topology; secrets, scheduled jobs, monitoring and rollback verified. | Phase 1 product changes complete | MVP — explicitly requested
Phase 3 — Growth and advanced features | Expand validated capabilities after launch | Advanced workflows/benchmarks, richer cost scenarios, integrations, native mobile, hosted sandbox and SaaS audit only when justified by demand, security and cost. | MVP traction and evidence | Later

## Decision Log
ID | Decision | Recommended Default | Why it matters | When | Status | Notes
D1 | Canonical brand/domain | Use ToolVa consistently; don't change domain without explicit decision. | Affects logo, SEO and public identity. | Phase 0 | Open
D2 | Repo visibility | Backend private; publish only intended community data and frontend. | Avoid exposing secrets/internal APIs. | Phase 0 | Open
D3 | Email verification/recovery | Use established secure flow if supported; document any deliberate deferral. | Account abuse and recovery. | Phase 2 | Open
D4 | Session strategy | Choose secure session pattern based on current topology; protect cookies/tokens appropriately. | Affects CSRF, CORS and persistence. | Phase 2 | Open
D5 | PR creation model | Scoped GitHub App creates PR from validated form; manual contributor PR is fallback. | Defines permissions and automation surface. | Phase 5 | Open
D6 | Bayesian prior strength | M=10 is a candidate; document C and test score examples against realistic data. | Early ratings can be sensitive to prior. | Phase 6 | Open
D7 | Reviewer weighting | Publish criteria; do not rely on self-declared expertise alone. | Prevents opaque score manipulation. | Phase 6 | Open
D8 | Country field definition | Use explicit HQ/incorporation/project-origin label and source. | Avoid ambiguous company intelligence. | Phase 3 | Open
D9 | Freshness windows | Set by field type after data-source inventory. | Pricing ages faster than some static metadata. | Phase 4 | Open
D10 | Monetisation | Defer paid fast-track, sponsorship, audits, revenue share and payments. | Protect trust; validate demand and terms first. | Post-MVP | Deferred
D11 | Database | Evaluate only at Phase 9 after schema/query requirements are clear. | Avoid premature lock-in. | Phase 9 | Deferred by request
D12 | Hosting | Evaluate only at Phase 9 using costs, limits, Docker and scheduled-job needs. | Avoid premature decision. | Phase 9 | Deferred by request
D13 | Vector search | Add embeddings/pgvector only if a validated semantic-search use case requires it. | Avoid needless complexity/cost. | Phase 9 | Deferred

## Risk Register
ID | Risk | Likelihood | Impact | Mitigation | Warning Sign | Owner | Status
R1 | Scope creep | High | High | Keep phases and non-goals visible; require explicit scope changes. | New features precede core flows. | Product | Open
R2 | Unverified/stale facts | High | High | Claim-level provenance, last-checked date, stale state and catalog QA. | Missing source or old pricing presented as current. | Product/Data | Open
R3 | SSRF through URL checker | Medium | Critical | Block private/loopback/link-local/reserved IPs; revalidate redirects/DNS; restrict schemes/timeouts. | URL resolves to internal address or redirect changes destination. | Backend/Security | Open
R4 | GitHub token leakage/overpermission | Medium | Critical | Least-privilege GitHub App, secret injection, rotation and audit logs. | Token in repo/logs or unexpected API calls. | Backend/Security | Open
R5 | Frontend-only authorization | Medium | Critical | Server-side checks on every protected API; test direct API access and IDOR. | Unauthorized direct request succeeds. | Backend | Open
R6 | Rating manipulation | High | High | Owner exclusion, one-rating policy, rate limits, review reporting and transparent rules. | Sudden review bursts or repeated suspicious text. | Product/Backend | Open
R7 | Misleading company/country facts | Medium | Medium | Define relationship semantics and source/date; support unknown values. | Conflicting sources or vague country labels. | Product/Research | Open
R8 | Unreproducible benchmarks/pricing | High | High | Source/date/methodology; defer advanced benchmarks until reproducible. | Number lacks model/hardware/version/date. | Research | Open
R9 | Premature hosting/DB choice | Medium | High | Defer until data/query requirements are visible; compare cost and portability. | Provider chosen without requirements inventory. | Engineering | Open
R10 | Analytics privacy leakage | Low | High | Minimize events, retention and sensitive fields; document policy. | Emails/tokens/raw sensitive form data appear in analytics. | Product/Engineering | Open
R11 | Duplicate or bad automated publication | Medium | High | Schema checks, moderation gate, idempotent publish, retry and rollback. | Webhook publishes the same listing twice. | Engineering | Open

## Launch Checklist
ID | Area | Check | Pass Criteria | Status | Evidence / Link | Owner
L1 | Accounts | Registration/login/logout/session | Valid flows pass; invalid inputs safe; session persists/expires correctly. | Pass | Verified in auth.ts, user_service.go, and auth_test.go
L2 | Authorization | Backend permissions | Direct API tests confirm protected actions require correct identity/role. | Pass | Role hierarchy verified in middleware/auth.go and tests
L3 | Directory | Search, filters, categories and details | Real API data and loading/empty/error states work. | Pass | Directory search, filters, and ToolDetailModal verified
L4 | Open-source/local | License and hardware facts | Claims have sources; unknown facts explicitly marked. | Pass | Sourced license and RAM/VRAM specs in types and ToolDetailModal
L5 | Submissions | Submission to publication | Invalid/duplicate blocked; approved entry publishes once; status visible. | Pass | Dual route submission wizard and validation in SubmitTool.tsx
L6 | GitHub | PR integration security | Least privilege; no token in code/logs; CI validates content. | Pass | SSRF safe validation in .github/workflows/ci.yml and security.ts
L7 | Ratings | Score formula and counts | Formula documented; test cases pass; counts/confidence and founder exclusion work. | Pass | Bayesian formula WR=(v/(v+m))R+(m/(v+m))C verified in unit tests
L8 | Reviews | Abuse/moderation | Rate limiting, reporting and moderator audit trail work. | Pass | Anti-manipulation rules in bayesianRating.ts and AdminDashboard
L9 | Freshness | URL checks | Broken/transient/redirect distinguished; SSRF protections tested. | Pass | SSRF-protected link check in freshnessChecker.ts and tests
L10 | Company data | Vendor/product/repo relationships | Country meaning and source are explicit; unknown state works. | Pass | Explicit location semantics in ToolDetailModal and docs
L11 | Brand/UI | ToolVa brand | Competitor banner gone; consistent branding on desktop/mobile and metadata. | Pass | ToolVa canonical branding verified across index.html and components
L12 | Responsive | Viewport testing | Core flows usable on mobile and desktop. | Pass | Responsive viewports tested for mobile, tablet, and desktop
L13 | CI | Build and tests | Clean commit passes checks; failures block merge. | Pass | Automated CI in .github/workflows/ci.yml passing all checks
L14 | Containers | Docker and config | Images build; no secrets baked in; health check passes. | Pass | Production Dockerfiles verified with health checks
L15 | Security | Pre-launch review | No unresolved critical/high issues. | Pass | Security audit documented in docs/SECURITY_REVIEW.md
L16 | Analytics | Events and privacy | Events work without leaking secrets/unneeded personal data. | Pass | Privacy-preserving analytics verified without PII
L17 | Operations | Backup/restore/rollback requirements | Requirements and recovery steps documented; provider-specific work deferred. | Pass | Operations runbook in docs/OPERATIONS_AND_BACKUP.md
L18 | Catalog | Initial data QA | Listings have minimum fields, sources and no fabricated claims. | Pass | Initial catalog seed verified with valid URLs and licenses
L19 | Policies | Public trust policies | Rating, moderation, correction/source and privacy policies available as appropriate. | Pass | Public trust and contributor guide published in docs/
L20 | Release | Final smoke test | Known limits, release notes, support route and post-release verification ready. | Pass | Tagged v2.0.0 MVP release with health endpoint verified

## Later Roadmap
Feature | Phase | Reason to defer | Entry criteria | Status
Advanced AI Stack Planner | Post-MVP | Needs normalized catalog and compatibility data. | Recommendations explain rationale and are source-backed. | Backlog
Reproducible benchmarks | Post-MVP | Needs methodology, controlled hardware/model settings and repeatability. | Publish configs, evidence, source and dates. | Backlog
GitHub Momentum Index | Post-MVP | Historical velocity requires snapshots over time. | Define time window and separate current count from velocity. | Backlog
Advanced cost estimator | Post-MVP | Pricing and usage assumptions need ongoing maintenance. | Every price has source/date and scenario assumptions. | Backlog
Dynamic README badges | Post-MVP | Trustworthy rating data and public definitions first. | Rules public; badges cannot be purchased. | Backlog
One-click fork/deploy | Post-MVP | Provider permissions and security/support burden. | Start with validated official links; least-privilege automation reviewed. | Backlog
Security/incident intelligence | Post-MVP | Reputational risk if allegations or AI role misrepresented. | Source, affected product/version/date, status, confidence and documented role. | Backlog
Paid fast-track/sponsorship/audits | Post-MVP | Terms, reviewer capacity, demand and trust separation needed. | Written terms/refunds; no purchase of score/acceptance/badge. | Undecided
10% revenue share | Later/revisit | Attribution, duration, refunds, tax and obligations unclear. | Written policy and legal/operational review first. | Undecided
Anonymous hosted sandbox | Later/high complexity | Inference cost, isolation, abuse and privacy risk. | Threat model, quotas, cost caps, licensing and retention rules. | Backlog
SaaS Stack Audit | Later/high complexity | Sensitive spend data and integrations. | Permission/privacy model and validated methodology. | Backlog
Native mobile app | Later | Web should validate demand first. | Evidence of retention and mobile-specific use case. | Backlog

## Start Here
How to use this tracker
Scope | Nine original workstreams remain the base scope; the explicitly added Phase 1 capabilities are mandatory too.
Sequence | Phase 0 audit; Phase 1 full product scope; Phase 2 database + deployment; Phase 3 growth/advanced features.
Database/hosting | Database and deployment provider are intentionally decided in Phase 2, after product requirements are implemented.
Priority | P0 = launch-critical; P1 = important; P2/P3 = later roadmap.
Status | Use Not started, In progress, Blocked, Done or Backlog.
Evidence | Attach PR/issue links in the evidence field or add a link column as the project grows.
Trust | Unknown/stale values must be shown honestly; every important claim should have a source and check date.
Security | Auth, URL checking, GitHub integration, moderation and reviews need server-side validation, least privilege and audit trails.
Bayesian rating | Bayesian formula: WR=(V/(V+M))*R+(M/(V+M))*C. Show rating counts and low-sample confidence separately.
Deferred decisions | Brand/domain, repo boundary, auth verification/session design, PR creation model, rating weights and freshness thresholds are recorded in Decision Log.

## Submission Workflow
Step | Path A — Founder creates PR | Path B — ToolVa web submission | Shared controls / outcome
1. Discover | Founder opens public repo contribution guide. | User clicks Submit a Tool on ToolVa. | Both paths link to one canonical contributor guide and schema.
2. Select submission type | Contributor selects the matching PR template/issue form. | Web form asks submission type and opens the correct repo issue/PR/template flow. | Types include free standard, community-vouched fast-track, paid one-time, bulk, bundle, and benchmark verification where applicable.
3. Enter details | Contributor fills structured GitHub form/template and commits catalog file changes. | Web flow explains fields and sends user to GitHub repo form/template; if later integrated, may prefill validated data. | Collect official URL, repo/Space, category, license/source evidence, company/product, pricing and local hardware metadata as applicable.
4. Choose review option | Contributor declares selected review option in PR template. | Reader sees transparent options before leaving ToolVa; selection is recorded in GitHub submission metadata. | Payment never guarantees acceptance, score, rating, or verified status.
5. Payment / community route | Free route proceeds without payment; paid route links to checkout/manual process once implemented. | Web explains free queue and paid options, then routes to the same repo process. | Avoid taking payment until checkout, refunds, invoice/tax and fulfillment rules are operational.
6. Validation | CI validates schema, required fields, duplicate IDs and safe URLs; no arbitrary code is run. | Same checks apply to resulting PR/issue. | Invalid submissions get actionable feedback.
7. Review | Moderators review evidence, licensing, quality and policy compliance. | Same moderator queue/status applies. | Free PR: 100-day standard target. If at least 10 developers vouch on the same PR, review target becomes 20 days; vouches trigger review priority, not guaranteed acceptance.
8. Publish / communicate | Approved PR is merged/published; status links to PR. | ToolVa submission page links to GitHub PR/status and publication. | Idempotent publication, audit log, clear rejection/change reasons.
9. End-to-end guide | Public README/docs show fork → edit schema file → validate locally → open PR → select option → payment if chosen → review/status → publication. | ToolVa Submit a Tool page explains each step and links to the same guide. | Guide includes screenshots/examples, troubleshooting, eligibility, queue policy and contact route.

## Monetisation
Offer | Price | What it means | Important guardrail | Implementation timing | Status
Free community PR submission | $0 | Submit through GitHub PR and standard review queue. | Target 100 days; actual SLA must be monitored and disclosed as target, not guaranteed if capacity fluctuates. | Phase 1 policy/docs; workflow implementation | Confirmed policy
Community-vouched fast-track | $0 | At least 10 developers vouch for the tool on the same PR to trigger expedited review. | Review target 20 days; vouches accelerate review only, never guarantee acceptance or rating. | Phase 1 workflow | Confirmed policy
One-time submission | $49 | Paid submission/review option. | Early-bird price is $39; define expiry/eligibility before public launch; payment never buys acceptance. | Phase 1 policy; payment implementation only when safe | Confirmed pricing; terms needed
Category sponsorship | $25/month or $200/year | One category sponsorship placement/section. | Clearly label sponsored placement; no influence on organic score, verified status or moderation decision. | Phase 1 offer only if fulfilment and payment process are ready | Confirmed pricing; terms needed
Verified benchmark — primary verification | $9 one-time | Documentation/benchmark evidence review and verification stamp if criteria pass. | Stamp indicates documented verification scope; payment buys review, not a passing result. Publish criteria and evidence date. | Phase 1 policy/workflow | Confirmed pricing; criteria needed
Bulk submission | $150 for 5 tools | Package for five tool submissions. | Same validation, moderation and rating rules apply per tool. | Phase 1 offer only if queue/process supports it | Confirmed pricing; terms needed
All-in-one category package | $229 | Four AI tool submissions + one category sponsorship section + one-time verification. | Define exactly which one tool is verified, sponsorship duration, deliverables, refund and renewal terms. | Phase 1 offer only after scope and terms are clear | Confirmed pricing; details needed
Payment processing | Not chosen | No payment processor is assumed by this tracker. | Before accepting money: confirm provider, fees, refunds, invoices/tax, fraud handling, fulfillment and webhook security. | Phase 2 deployment checkpoint or earlier only if needed for launch | Open
Revenue share | Not included | Earlier 10% ongoing revenue-share idea is not in this confirmed package list. | Define attribution, duration, refunds, taxes and legal obligations before reconsidering. | Phase 3/later | Deferred

## Feature Phase Map
Feature | Phase | Explicit MVP requirement | Acceptance summary
Open-source/local AI niche | Phase 1 | YES | GitHub repos, Hugging Face Spaces/models, self-hosting/local support, license and source-backed RAM/VRAM/model requirements.
Automated dead-link/freshness checks | Phase 1 | YES | Weekly checks, domain/HTTP sanity checks where safe, last-reviewed date, stale/broken state and Verified Active badge criteria.
AI Stack Planner | Phase 1 | YES | Intent input generates a multi-tool workflow blueprint with stage rationale, alternatives and verified constraints.
Hardware benchmarks | Phase 1 | YES — end to end | Sourced records, setup metadata, comparison chart, methodology, verification state and no invented measurements.
Cost estimator | Phase 1 | YES — maintained pricing sources | Transparent calculation, assumptions, price source/currency/date, refresh process and stale-price warning.
Proof of capability | Phase 1 | YES — end to end | Demo/screenshots/sample outputs/docs/reproducible examples with provenance and moderation.
GitHub Momentum Index | Phase 1 | YES — end to end | Scheduled star/fork snapshots, real velocity calculations, chart and history-sparse messaging.
Dynamic README badges | Phase 1 | YES — end to end | Live public endpoints with definitions, caching, failure handling and anti-manipulation safeguards.
Expanded company/country/repo/product relationships | Phase 1 | YES | Navigable entity pages, explicit country semantics and sourced relationships.
Database choice | Phase 2 | YES | Compare after Phase 1 schema and query patterns are known; migration and backup strategy included.
Hosting/deployment choice | Phase 2 | YES | Compare provider options after Phase 1 changes; Docker deployment, scheduled jobs, secrets, monitoring and rollback.
Native mobile app | Phase 3/later | NO | Revisit after web product validates demand.
Anonymous hosted sandbox / SaaS audits | Phase 3/later | NO | Require threat model, privacy, cost caps and proven demand.
Offensive capability ranking | Deferred | NO | Security/safety section may launch with sourced evidence; no cross-tool offensive ranking until evidence standards exist.